## issuelog
WCPM | Communications Plan |  |  |  | Project R | [5 empty] | 2026-07-28
Populations
Comm Ref | Information or Message | Method | Originator / Source | Timing | Result | Sponsors | Team Members | End-Users | Call Centre | Program-mers | General Workforce | External
| Case For Change | Sponsorship Cascade | PM > CEO | Project Start | Complete | All | All | All | All | All | All
| Project Admin procedures | Handbook & team-leader briefing | PMO | On induction | On-going |  | All
| Programming standards |  | Senior Programmer > PMO | Project Start | [5 empty] | All
| Reference Info | Knowledge Base on Intranet | Documentation Team | Complete by start of end-user training |  |  |  | All | All
| Tidy up current data | Sponsorship cascade | PM > CEO | Second tranche - Project Startup plus 1 month |  |  |  | All
| Your bill will be changing | Insert with bills | Customer Services Manager | 3 months before go live thru live date | [7 empty] | Customers
| New billing proces and procedures | Training Module | Training Team Leader | 4 weeks before go-live |  |  |  | Accounts Dept | All
| Organisational restructuring in Accounts Dept | Sponsorship cascade | PM > CEO | 6 months before go-live | [6 empty] | All
| Organisational restructuring in Accounts Dept - Details | Accounts Departmental Meeting | FD / Chief Accountant | 6 months before go-live | [6 empty] | Accounts Department
| Internal promotion | Company Newsletter | Change Manager > Internal Comms Department | 6 weeks before go-live | [6 empty] | All UK staff